## Scoreboard
Delivery Scoreboard, per owner. Kurt only.
Private file: individual scores are not shared between team members. The shared tracker stays the team view of the work itself.
Ivan, Jul call: was it delivered on time, yes, no, or faster; was it delivered at the level you expected. Resyncs are the quality signal. Computed from the Delivery Log tab.
Owner | Committed (Due set) | Delivered | Faster | On time | Late | On time or faster | Overdue (open) | Avg resyncs
JV Manlangit | 0 | 2 | 0 | 0 | 0 | - | 0 | -
Anton Betia | 1 | 0 | 0 | 0 | 0 | - | 0 | -
Manzil Balani | 0 | 1 | 0 | 0 | 0 | - | 0 | -
Elias Marcella | 0 | 0 | 0 | 0 | 0 | - | 0 | -
Jastin Lagumbay | 0 | 0 | 0 | 0 | 0 | - | 0 | -
Team | 1 | 3 | 0 | 0 | 0 | - | 0
How to read it: Committed = rows with an agreed Due date. Speed needs Due dates, so set them at standup; a delivery without a Due date cannot be scored.
Refresh weekly: copy rows A4 down to M from the tracker's Master Rollup and paste into the Delivery Log tab (same columns). In Google Sheets, the Delivery Log tab can be replaced with IMPORTRANGE for auto-sync.
Feeds the quarterly Revolut-style scorecard: Speed from on time or faster, Quality from resyncs and level delivered, Complexity judged per project. Deliverables = (Speed + Quality) x Complexity.
Formulas:
Overdue (open) = SUMPRODUCT(('Delivery Log'!$A4:A400=[Owner])*('Delivery Log'!$H4:H400<>"")*('Delivery Log'!$I4:I400="")*('Delivery Log'!$C4:C400<>"Completed")*('Delivery Log'!$C4:C400<>"Cancelled")*('Delivery Log'!$H4:H400<TODAY()))

## Delivery Log
Mirror of the tracker Master Rollup (columns A to M). Refresh by paste, or IMPORTRANGE in Google Sheets. The Scoreboard reads Owner (A), Status (C), Due (H), Delivered (I), Resyncs (K).
Owner | Project | Status | Priority | KPI Key Driver | Impact (bottom-up) | Added | Due | Delivered | Speed | Resyncs | Summary | ClickUp / BRD Link
JV Manlangit | SAP Video Capture | In Progress | Urgent | SAP - D2 Disbursement per active agent | [6 empty] | Video statement capture for high-risk clients with AI transcript + facial verification. Phase 1 live. AI status update pending. | https://app.clickup.com/t/86ewdm810
Anton Betia | Item-Based Pricing | Blocked | Urgent | Pricing - Merchants (Chi) | [6 empty] | Apply promo rules to selected products, not whole catalog. Part of products engine. awaiting merchant requirements. | https://app.clickup.com/t/86ewdm7xz
Elias Marcella | Credit Line (Launch) | In Progress | Urgent | Credit Line - D1 Utilization & drawdown | CL utilization and drawdown, target set ~30 days post-launch | [5 empty] | Launched 15 Jul (F&F/ETB). Phase-1 open: repayment/statement emails, eligibility, biz events, web FAQ, pending-txn spec. Refund/chargeback & IPP later phases. | https://app.clickup.com/t/9008174123/86eyaav7k
JV Manlangit | Motorcycle Loans (KServico) | In Progress | High | Motorcycles - D1 Moto monthly disbursement | Moto monthly run rate, gated by Nhat | [5 empty] | Addendum & SA guide done, delivered via SAP. refresher pending. return-config changes being finalized. | https://app.clickup.com/t/9008174123/86ey83p6c
Anton Betia | Special Deals Offer to Low-Risk Customers | In Progress | High | Deals - D1 Monthly disbursement | Conversion lift on low-risk base, size with Nhat before comms |  | 2026-07-20 |  |  |  | Additional-limit offer to low-risk clients to lift conversion. DE deployed. comms Jul 20. | https://app.clickup.com/t/9008174123/86exz94uf
Anton Betia | Deals API Documentation | In Progress | High | Deals - D1 Monthly disbursement | [6 empty] | Gather partner API docs (Giftaway, 3Cat) to scope integration timeline. | https://app.clickup.com/t/9008174123/86ey90pqa
Anton Betia | Vouchers on Deals | In Progress | High | Deals - D1 Monthly disbursement | [6 empty] | Enable voucher purchases on Deals. preparing rails. | https://app.clickup.com/t/9008174123/86eyadmt7
Anton Betia | Launch Deals on Web | In Progress | High | Deals - D3 Delivery on roadmap | [6 empty] | Web version of Deals. Phase 1 UI testing paused as of Jul 15.
Manzil Balani | Deals Merchant BD Pipeline | In Progress | High | Deals BD - D2 New merchants live & disbursing | New merchants live and disbursing, ticket uplift | [5 empty] | Brand pipeline. WARM: Kimstore, 3Cat, Hati, Laptop Factory, Samsung, PrimerGrp, PowerMac, AirAsia, Qoala. Rejected: MetroMart, Engkanto, DataBlitz, Vivo, Mandaue Foam. | https://docs.google.com/spreadsheets/d/1Qx9NB9uO7TvVACgTXQszWOwBFCa_OTElUIsEwWYCVOM/
Elias Marcella | Access Card | In Progress | High | Card - D2 Card unit economics | Per-card break-even on interchange at target CAC | [5 empty] | BillEase Mastercard (numberless) w/ AUB & MatchMove. MOA negotiation (audit cap, CS cert, VAPT). design + bureau RFPs out. activation BRD done. Target prod Q4 2026. | https://docs.google.com/spreadsheets/d/1Vf8kaBSoQp1PeSw156nCNtYON_3ZJM5ZbR9xZPe8SjU/
Elias Marcella | Risk-Based Pricing | Blocked | High | Pricing - Merchants/Risk | [6 empty] | Dynamic interest rates by client credit behaviour. Part of products engine. awaiting requirements. | https://app.clickup.com/t/86ewn2hpd
Jastin Lagumbay | SM Appliances - Acknowledgement Receipt | In Progress | High | Merchant Onboarding - D2 Onboarding cycle time | [6 empty] | Read-only approved-transaction receipt for merchants (75%). Dev done. awaiting SM signatory. | https://app.clickup.com/t/86ewpkfpv
Jastin Lagumbay | Supervisors/RMs Stamp in Create Trx Report | In Progress | High | Merchant Onboarding - D2 Onboarding cycle time | [6 empty] | Adds supervisor/RM stamp to Create Trx Report (83%). Live for txns after Jun 16. validating incentives. | https://app.clickup.com/t/86ex68b0u
Jastin Lagumbay | QRPh Chargeback Escalation (Netbank/AUB) | In Progress | High | QRPh - D1 Monthly disbursement run rate | Protects the QRPh run rate | [5 empty] | Daily QRPh chargeback escalation & checking for AUB and Netbank. | https://app.clickup.com/t/9008174123/86ey9ztg7
Jastin Lagumbay | Merchant Onboarding Ops Queue (BAU) | In Progress | High | Merchant Onboarding - D2 Onboarding cycle time | [6 empty] | Daily BAU queue: shop/user/bank adds, onboarding, branch/name changes. ~20+ tickets/week, mostly same/next-day. | https://docs.google.com/spreadsheets/d/1FXbhtIl3aNyH9zr5Zf_xpV_OaLrUeQVwTLEMQKsn_dg/
Jastin Lagumbay | Product Pricing / SAP Calculator PVT | In Progress | High | IT/PVT - Billy (D1 release quality gate) | [6 empty] | Pricing/tenor/IR validation across merchant scenarios (Android/iOS). Recent Fails at FC Home Lubao 3 & Shaw need config fix. | https://docs.google.com/spreadsheets/d/178O3aMK18zV_j96Xbp6UD3-QWxWX9QIFjTOju0fw-sM/
JV Manlangit | Promoter Referral Program v2: Online Linking | In Progress | Normal | SAP - D2 Disbursement per active agent | [6 empty] | Extends referral program to online transactions. BRD in progress. validation shifting to Merchants/Billease. | https://app.clickup.com/9008174123/v/dc/8cevn1b-45778/8cevn1b-224358
JV Manlangit | Feedback Form for Non-Converted Sign-ups | In Progress | Normal | SAP - D2 Disbursement per active agent | [6 empty] | Captures friction on agents' unconverted leads (25%). Adding conditional-question feature. | https://app.clickup.com/t/86ewphrkt
JV Manlangit | SAP Calculator | In Progress | Normal | SAP - D2 Disbursement per active agent | [6 empty] | Real-time SAP loan calculator from product config (40%). Mockup + ticket done. dev pending. | https://app.clickup.com/t/86ex68cg9
JV Manlangit | SAP Looker Dashboard | In Progress | Normal | BI - Jenny Ho (D1 dashboard) | [6 empty] | Looker reporting for Trx Requests, Non-Converted Sign-ups & future SAP projects (50%). Dev pending. | https://app.clickup.com/t/86ewqfqqa
Anton Betia | Deals UX Study | In Progress | Normal | Deals - D2 Acceptance/conversion | [6 empty] | UX study: brand-first vs agnostic Deals store. Regroup call scheduled.
Anton Betia | Multi-item per Merchant | In Progress | Normal | Deals - D1 Monthly disbursement | [6 empty] | Same product across merchants with price-comparison screen. BRD drafted. design pending. | https://app.clickup.com/t/9008174123/86ey9gdq1
Anton Betia | Location-Based Delivery | In Progress | Normal | Deals - D1 Monthly disbursement | [6 empty] | Support coordinates + flag out-of-range deliveries. BRD + mockup for Kurt's input. | https://app.clickup.com/t/9008174123/86eyavqf4
Anton Betia | Pick-Up Model | In Progress | Normal | Deals - D1 Monthly disbursement | [6 empty] | Pickup-location fulfillment option instead of delivery. BRD + mockup for Kurt's input. | https://app.clickup.com/t/9008174123/86eyavtqg
Anton Betia | Support for Pre-Owned on Deals | Not Started | Normal | Deals - D1 Monthly disbursement | [6 empty] | Prepare rails for pre-owned listings (3Cat). Rails list being scoped. | https://app.clickup.com/t/9008174123/86eyafcd5
Anton Betia | Credit Line for Deals | Not Started | Normal | Deals - D1 Monthly disbursement | [6 empty] | Integrate Deals with Credit Line. Target August. | https://app.clickup.com/t/9008174123/86ey7mar5
Anton Betia | Deals 360 Dashboard | Not Started | Normal | BI - Jenny Ho (D1 dashboard) | [6 empty] | Expanded Deals 360 dashboard. requested columns from Jenny. | https://app.clickup.com/t/9008174123/86ey90puc
Manzil Balani | Adding Missing Deals Items | In Progress | Normal | Deals BD - D2 New merchants live | [6 empty] | Add products missing from Deals inventory. List provided. items pending.
Jastin Lagumbay | Integrate Merchant Guide to Billease Docs | Not Started | Normal | Merchant Onboarding - D2 Onboarding cycle time | Fewer onboarding tickets via self-serve guide | [5 empty] | Single self-service Merchant Guide: handbook + 7 walkthroughs, vector screens, PII redaction. Target 30% fewer tickets. | https://app.clickup.com/t/9008174123/86exz70h6
Jastin Lagumbay | Automate Onboarding Email | Not Started | Normal | Merchant Onboarding - D2 Onboarding cycle time | [6 empty] | Auto welcome email on first transition to Active (once only), with logging + retry. | https://app.clickup.com/t/9008174123/86ev2ktw2
Jastin Lagumbay | Update 'How to Become a Merchant' Page | Not Started | Normal | Merchant Onboarding - D2 Onboarding cycle time | [6 empty] | Add rejection screen linking to QRPh FAQs. keep success screen largely the same. | https://app.clickup.com/t/9008174123/86ey3qbz2
JV Manlangit | SAP Announcement & Quiz Module v2 | In Progress | Low | SAP - D2 Disbursement per active agent | [6 empty] | v1 enhancements: editable-after-activation, duplicate forms, data filter by TL & SFT.
JV Manlangit | SAP Announcement & Quiz Module v1 | Completed | Urgent | SAP - D2 Disbursement per active agent |  |  |  | 2026-07-03 | - |  | Mandatory in-SAP info delivery + retention quiz per agent. Rolled to prod Jul 3. | https://app.clickup.com/t/9008174123/86ey0ujv3
JV Manlangit | Early Upsell | Completed | Urgent | SAP - D2 Disbursement per active agent | [6 empty] | Post-disbursement upsell leaflet + announcement/quiz. Live. ~94% completion as of Jul 10.
JV Manlangit | Credit Line - Agent Announcement (SAP) | Completed | Urgent | SAP - D2 Disbursement per active agent |  |  |  | 2026-07-16 | - |  | Credit Line announcement + quiz delivered to agents via SAP Jul 16.
JV Manlangit | Promoter Referral Program v1: Offline Linking | Completed | High | SAP - D2 Disbursement per active agent | [6 empty] | Auto-rewards promoters for merchant-loan referrals (offline). Live. Giftaway credits monitored weekly. | https://app.clickup.com/9008174123/v/dc/8cevn1b-45778/8cevn1b-219678
Manzil Balani | Maxicare PRIMA Launch on Deals | Completed | High | Deals BD - D2 New merchants live |  |  |  | 2026-07-10 | - |  | Maxicare PRIMA live on Deals Jul 10. first marketing blast Jul 21. iOS pending shorter descriptions.
Anton Betia | Adding Pay Later on Deals | Cancelled | Low | Deals - D1 Monthly disbursement | [6 empty] | Pay Later / convert-to-installment on Deals. Cancelled - redundant with Credit Line. | https://app.clickup.com/t/9008174123/86ew51ha3
Anton Betia | Apply Promo at Category/Item Level | Cancelled | Low | Deals - D1 Monthly disbursement | [6 empty] | Item/category-level promos. Deferred - to be built after the Product Engine (Chi). | https://app.clickup.com/t/9008174123/86ey2gvyt

## Initiative Log
Initiative Log: the growth dimension (not bonus)
Ivan, Jul call: you cannot grow if you do not do initiatives. Track who connects the numbers to actions. Assess each idea easy vs difficult and high vs low impact; it gets its own priority; then run it.
Date | Person | Initiative (problem, proposed action) | Effort | Impact | Priority (auto) | Status | Notes
2026-07-20 | Anton Betia | Deals listing sorts P9,999 item first while the popular P1,000 item is last; add cheapest-first sorting | Easy | High | P1 do now | In tracker | Raised by Ivan on the Jul call; Kurt committed the fix

## Calibration
Calibration: one score per person (5 to 1)
Run NOW for the past 3 months; do not wait for the December review (Ivan, Jul call). Compare the result to your gut feel; when it corresponds, adopt it. How you arrive at the score, no one cares; the score is what calibrates.
The bar is the person, not the peer: "I am not comparing you with him. I am comparing your bar with your performance." Juniors get a mistake discount; non-juniors must arrive fully thought through.
Person | Seniority (the bar) | On time or faster | Avg resyncs | Initiatives | Scorecard overall grade | Score (5-1) | Notes / evidence
JV Manlangit |  | - | - | 0
Anton Betia |  | - | - | 1
Manzil Balani |  | - | - | 0
Elias Marcella | Senior | - | - | 0
Jastin Lagumbay |  | - | - | 0
Seniority for Elias per Ivan: superstar bar, well paid, the only discount is domain knowledge. Set the rest of the bars yourself and confirm with Ivan.
Scorecard overall grade comes from each person's QuantumLight Product Owner scorecard (one copy per person per quarter). Yellow = fill by hand.