## README
Executive Project Tracker v2, POS Product Team (H2 2026)
One file, shared with the whole team. One tab per owner plus a consolidated Master. Linked to the PBT Metric Tree.
How the team is measured (agreed with Ivan, Jul call)
PMs are not scored on hitting line volumes. Volume and PBT numbers are management-owned; the team is not punished for them ("they are not magicians"). Sales-style volume KPIs belong to the network team; our target is profit, and sometimes less sales means more profit.
What PMs own and are scored on is DELIVERY of the agreed projects: Speed (on time, or faster) and Quality (delivered at the expected level, thought through, minimal resyncs). The bar is the person's seniority: juniors get a mistake discount, non-juniors must deliver magic. "I am not comparing you with him. I am comparing your bar with your performance."
Initiative is the third dimension, assessed for growth, not for bonus: does the person know their numbers cold and connect problems to actions, bringing prioritized initiatives (easy vs difficult, high vs low impact).
Purpose
One row per project, straight to the point. ClickUp stays the main working document and source of truth.
This sheet is the executive-level view: what the project is, whether it is moving, what it is expected to move (Impact), and whether we delivered when we said we would.
Everyone sees everything here. The point is a single, centralized view of what the team is doing.
The columns
Project, Status, Priority, KPI Key Driver, Impact (bottom-up), Added, Due, Delivered, Speed, Resyncs, Summary, ClickUp or BRD Link. The Master also has an Owner column.
Added = the date the project entered the tracker. Due = the date agreed with the owner. Delivered = the date it actually shipped.
Speed is automatic from Due vs Delivered: Faster, On time, or Late. A dash means it was delivered without an agreed Due date; set Due dates so Speed can be scored.
Resyncs counts how many times the work bounced back for rework or another sync. It is the quality proxy: a well-thought-through delivery needs no repeated syncs (Ivan: "if I have to resync and come back again and again, the quality goes down automatically").
Status and Priority are dropdowns. Yellow cells are blanks the owner must fill: Impact, Added and Due before a project enters In Progress; Delivered when it ships.
In Google Sheets, Added and Delivered can be stamped automatically with a small onEdit script (see team-performance/src in the repo), or with iterative-calculation formulas.
Status and Priority values
Status: Not Started, In Progress, Blocked, Completed, Cancelled.
Priority: Urgent, High, Normal, Low.
Ranking rule
Rows are ordered Urgent, High, Normal, Low, with Completed and Cancelled sent to the bottom.
Operating cadence
Weekly standup: walk the Master top-down, blocked and overdue first, update Due, Delivered and Resyncs. Details live in ClickUp via the link column.
Monthly: KPI readout on the KPI Targets H2 tab against Nhat's PBT-per-line model and Jenny's metric-tree dashboard. Context for everyone; scoring for no one.
Quarterly: individual reviews on the QuantumLight (Revolut) Product Owner scorecard, graded against the seniority talent bar. Speed and Resyncs here are the evidence. Kurt runs a retro review for the past 3 months now rather than waiting for December (Ivan, Jul call).
Lock each tab to one person (done inside Google Sheets)
1. Share the whole file with the 5 owners as Editor, and the wider team as Viewer.
2. On each owner tab, use Data, then Protect sheets and ranges, then Set permissions, then Custom.
3. Add only that owner's email plus your own, then Done.
Design
Minimalist, per the Billease brand: white-dominant, structural blue 203AA9 headers, ink text, rationed color.

## Master Rollup
Master Rollup: all projects, ranked (Urgent, High, Normal, Low, done at bottom). Team = Viewer. Yellow = owner to fill. Speed is automatic.
Owner | Project | Status | Priority | KPI Key Driver | Impact (bottom-up) | Added | Due | Delivered | Speed | Resyncs | Summary | ClickUp / BRD Link
JV Manlangit | SAP Video Capture | In Progress | Urgent | SAP - D2 Disbursement per active agent | [6 empty] | Video statement capture for high-risk clients with AI transcript + facial verification. Phase 1 live. AI status update pending. | https://app.clickup.com/t/86ewdm810
Anton Betia | Item-Based Pricing | Blocked | Urgent | Pricing - Merchants (Chi) | [6 empty] | Apply promo rules to selected products, not whole catalog. Part of products engine. awaiting merchant requirements. | https://app.clickup.com/t/86ewdm7xz
Elias Marcella | Credit Line (Launch) | In Progress | Urgent | Credit Line - D1 Utilization & drawdown | CL utilization and drawdown, target set ~30 days post-launch | [5 empty] | Launched 15 Jul (F&F/ETB). Phase-1 open: repayment/statement emails, eligibility, biz events, web FAQ, pending-txn spec. Refund/chargeback & IPP later phases. | https://app.clickup.com/t/9008174123/86eyaav7k
JV Manlangit | Motorcycle Loans (KServico) | In Progress | High | Motorcycles - D1 Moto monthly disbursement | Moto monthly run rate, gated by Nhat | [5 empty] | Addendum & SA guide done, delivered via SAP. refresher pending. return-config changes being finalized. | https://app.clickup.com/t/9008174123/86ey83p6c
Anton Betia | Special Deals Offer to Low-Risk Customers | In Progress | High | Deals - D1 Monthly disbursement | Conversion lift on low-risk base, size with Nhat before comms |  | 2026-07-20 |  |  |  | Additional-limit offer to low-risk clients to lift conversion. DE deployed. comms Jul 20. | https://app.clickup.com/t/9008174123/86exz94uf
Anton Betia | Deals API Documentation | In Progress | High | Deals - D1 Monthly disbursement | [6 empty] | Gather partner API docs (Giftaway, 3Cat) to scope integration timeline. | https://app.clickup.com/t/9008174123/86ey90pqa
Anton Betia | Vouchers on Deals | In Progress | High | Deals - D1 Monthly disbursement | [6 empty] | Enable voucher purchases on Deals. preparing rails. | https://app.clickup.com/t/9008174123/86eyadmt7
Anton Betia | Launch Deals on Web | In Progress | High | Deals - D3 Delivery on roadmap | [6 empty] | Web version of Deals. Phase 1 UI testing paused as of Jul 15.
Manzil Balani | Deals Merchant BD Pipeline | In Progress | High | Deals BD - D2 New merchants live & disbursing | New merchants live and disbursing, ticket uplift | [5 empty] | Brand pipeline. WARM: Kimstore, 3Cat, Hati, Laptop Factory, Samsung, PrimerGrp, PowerMac, AirAsia, Qoala. Rejected: MetroMart, Engkanto, DataBlitz, Vivo, Mandaue Foam. | https://docs.google.com/spreadsheets/d/1Qx9NB9uO7TvVACgTXQszWOwBFCa_OTElUIsEwWYCVOM/
Elias Marcella | Access Card | In Progress | High | Card - D2 Card unit economics | Per-card break-even on interchange at target CAC | [5 empty] | BillEase Mastercard (numberless) w/ AUB & MatchMove. MOA negotiation (audit cap, CS cert, VAPT). design + bureau RFPs out. activation BRD done. Target prod Q4 2026. | https://docs.google.com/spreadsheets/d/1Vf8kaBSoQp1PeSw156nCNtYON_3ZJM5ZbR9xZPe8SjU/
Elias Marcella | Risk-Based Pricing | Blocked | High | Pricing - Merchants/Risk | [6 empty] | Dynamic interest rates by client credit behaviour. Part of products engine. awaiting requirements. | https://app.clickup.com/t/86ewn2hpd
Jastin Lagumbay | SM Appliances - Acknowledgement Receipt | In Progress | High | Merchant Onboarding - D2 Onboarding cycle time | [6 empty] | Read-only approved-transaction receipt for merchants (75%). Dev done. awaiting SM signatory. | https://app.clickup.com/t/86ewpkfpv
Jastin Lagumbay | Supervisors/RMs Stamp in Create Trx Report | In Progress | High | Merchant Onboarding - D2 Onboarding cycle time | [6 empty] | Adds supervisor/RM stamp to Create Trx Report (83%). Live for txns after Jun 16. validating incentives. | https://app.clickup.com/t/86ex68b0u
Jastin Lagumbay | QRPh Chargeback Escalation (Netbank/AUB) | In Progress | High | QRPh - D1 Monthly disbursement run rate | Protects the QRPh run rate | [5 empty] | Daily QRPh chargeback escalation & checking for AUB and Netbank. | https://app.clickup.com/t/9008174123/86ey9ztg7
Jastin Lagumbay | Merchant Onboarding Ops Queue (BAU) | In Progress | High | Merchant Onboarding - D2 Onboarding cycle time | [6 empty] | Daily BAU queue: shop/user/bank adds, onboarding, branch/name changes. ~20+ tickets/week, mostly same/next-day. | https://docs.google.com/spreadsheets/d/1FXbhtIl3aNyH9zr5Zf_xpV_OaLrUeQVwTLEMQKsn_dg/
Jastin Lagumbay | Product Pricing / SAP Calculator PVT | In Progress | High | IT/PVT - Billy (D1 release quality gate) | [6 empty] | Pricing/tenor/IR validation across merchant scenarios (Android/iOS). Recent Fails at FC Home Lubao 3 & Shaw need config fix. | https://docs.google.com/spreadsheets/d/178O3aMK18zV_j96Xbp6UD3-QWxWX9QIFjTOju0fw-sM/
JV Manlangit | Promoter Referral Program v2: Online Linking | In Progress | Normal | SAP - D2 Disbursement per active agent | [6 empty] | Extends referral program to online transactions. BRD in progress. validation shifting to Merchants/Billease. | https://app.clickup.com/9008174123/v/dc/8cevn1b-45778/8cevn1b-224358
JV Manlangit | Feedback Form for Non-Converted Sign-ups | In Progress | Normal | SAP - D2 Disbursement per active agent | [6 empty] | Captures friction on agents' unconverted leads (25%). Adding conditional-question feature. | https://app.clickup.com/t/86ewphrkt
JV Manlangit | SAP Calculator | In Progress | Normal | SAP - D2 Disbursement per active agent | [6 empty] | Real-time SAP loan calculator from product config (40%). Mockup + ticket done. dev pending. | https://app.clickup.com/t/86ex68cg9
JV Manlangit | SAP Looker Dashboard | In Progress | Normal | BI - Jenny Ho (D1 dashboard) | [6 empty] | Looker reporting for Trx Requests, Non-Converted Sign-ups & future SAP projects (50%). Dev pending. | https://app.clickup.com/t/86ewqfqqa
Anton Betia | Deals UX Study | In Progress | Normal | Deals - D2 Acceptance/conversion | [6 empty] | UX study: brand-first vs agnostic Deals store. Regroup call scheduled.
Anton Betia | Multi-item per Merchant | In Progress | Normal | Deals - D1 Monthly disbursement | [6 empty] | Same product across merchants with price-comparison screen. BRD drafted. design pending. | https://app.clickup.com/t/9008174123/86ey9gdq1
Anton Betia | Location-Based Delivery | In Progress | Normal | Deals - D1 Monthly disbursement | [6 empty] | Support coordinates + flag out-of-range deliveries. BRD + mockup for Kurt's input. | https://app.clickup.com/t/9008174123/86eyavqf4
Anton Betia | Pick-Up Model | In Progress | Normal | Deals - D1 Monthly disbursement | [6 empty] | Pickup-location fulfillment option instead of delivery. BRD + mockup for Kurt's input. | https://app.clickup.com/t/9008174123/86eyavtqg
Anton Betia | Support for Pre-Owned on Deals | Not Started | Normal | Deals - D1 Monthly disbursement | [6 empty] | Prepare rails for pre-owned listings (3Cat). Rails list being scoped. | https://app.clickup.com/t/9008174123/86eyafcd5
Anton Betia | Credit Line for Deals | Not Started | Normal | Deals - D1 Monthly disbursement | [6 empty] | Integrate Deals with Credit Line. Target August. | https://app.clickup.com/t/9008174123/86ey7mar5
Anton Betia | Deals 360 Dashboard | Not Started | Normal | BI - Jenny Ho (D1 dashboard) | [6 empty] | Expanded Deals 360 dashboard. requested columns from Jenny. | https://app.clickup.com/t/9008174123/86ey90puc
Manzil Balani | Adding Missing Deals Items | In Progress | Normal | Deals BD - D2 New merchants live | [6 empty] | Add products missing from Deals inventory. List provided. items pending.
Jastin Lagumbay | Integrate Merchant Guide to Billease Docs | Not Started | Normal | Merchant Onboarding - D2 Onboarding cycle time | Fewer onboarding tickets via self-serve guide | [5 empty] | Single self-service Merchant Guide: handbook + 7 walkthroughs, vector screens, PII redaction. Target 30% fewer tickets. | https://app.clickup.com/t/9008174123/86exz70h6
Jastin Lagumbay | Automate Onboarding Email | Not Started | Normal | Merchant Onboarding - D2 Onboarding cycle time | [6 empty] | Auto welcome email on first transition to Active (once only), with logging + retry. | https://app.clickup.com/t/9008174123/86ev2ktw2
Jastin Lagumbay | Update 'How to Become a Merchant' Page | Not Started | Normal | Merchant Onboarding - D2 Onboarding cycle time | [6 empty] | Add rejection screen linking to QRPh FAQs. keep success screen largely the same. | https://app.clickup.com/t/9008174123/86ey3qbz2
JV Manlangit | SAP Announcement & Quiz Module v2 | In Progress | Low | SAP - D2 Disbursement per active agent | [6 empty] | v1 enhancements: editable-after-activation, duplicate forms, data filter by TL & SFT.
JV Manlangit | SAP Announcement & Quiz Module v1 | Completed | Urgent | SAP - D2 Disbursement per active agent |  |  |  | 2026-07-03 | - |  | Mandatory in-SAP info delivery + retention quiz per agent. Rolled to prod Jul 3. | https://app.clickup.com/t/9008174123/86ey0ujv3
JV Manlangit | Early Upsell | Completed | Urgent | SAP - D2 Disbursement per active agent | [6 empty] | Post-disbursement upsell leaflet + announcement/quiz. Live. ~94% completion as of Jul 10.
JV Manlangit | Credit Line - Agent Announcement (SAP) | Completed | Urgent | SAP - D2 Disbursement per active agent |  |  |  | 2026-07-16 | - |  | Credit Line announcement + quiz delivered to agents via SAP Jul 16.
JV Manlangit | Promoter Referral Program v1: Offline Linking | Completed | High | SAP - D2 Disbursement per active agent | [6 empty] | Auto-rewards promoters for merchant-loan referrals (offline). Live. Giftaway credits monitored weekly. | https://app.clickup.com/9008174123/v/dc/8cevn1b-45778/8cevn1b-219678
Manzil Balani | Maxicare PRIMA Launch on Deals | Completed | High | Deals BD - D2 New merchants live |  |  |  | 2026-07-10 | - |  | Maxicare PRIMA live on Deals Jul 10. first marketing blast Jul 21. iOS pending shorter descriptions.
Anton Betia | Adding Pay Later on Deals | Cancelled | Low | Deals - D1 Monthly disbursement | [6 empty] | Pay Later / convert-to-installment on Deals. Cancelled - redundant with Credit Line. | https://app.clickup.com/t/9008174123/86ew51ha3
Anton Betia | Apply Promo at Category/Item Level | Cancelled | Low | Deals - D1 Monthly disbursement | [6 empty] | Item/category-level promos. Deferred - to be built after the Product Engine (Chi). | https://app.clickup.com/t/9008174123/86ey2gvyt

## KPI Targets H2
KPI Targets H2 2026, per line (Tier 0 / Tier 1). Management-owned context.
These numbers are owned by management (Ivan + Kurt, fed by Nhat's model and Jenny's dashboard). The team is NOT scored or punished on these outcomes; every PM must know their line cold and connect problems to actions. PM scoring lives in delivery (Speed x Quality on the tracker). Yellow = set with Ivan or fill monthly.
Line outcomes, monthly volume (PHP M disbursement)
Line | Phase | PM (context) | Jul | Aug | Sep | Oct | Nov | Dec | YTD att. | Basis / notes
QRPh disbursement | Star | Jastin | [7 empty] | Run-rate to confirm with Ivan. Hold and defend the star line (chargebacks, onboarding cycle time).
actual | [8 empty] | -
Deals disbursement | Question | Anton + Manzil | [7 empty] | Staged monthly ramp at positive NPM. Stage sizes and timing set by management; the reject-salvage plan sizes the ramp.
actual | [8 empty] | -
Moto (KServico) | Question | JV | [7 empty] | Run-rate gated by Nhat's unit-economics check.
actual | [8 empty] | -
Deals, managed accounts | Question | Manzil | [7 empty] | ProTech, Maxicare, 3Cat. Maxicare live: soft launch first week, marketing on this week.
actual | [8 empty] | -
Credit Line (utilization %, target set ~30 days post-launch)
Line | Phase | PM (context) | Jul | Aug | Sep | Oct | Nov | Dec | YTD att. | Basis / notes
CL utilization / drawdown | New launch | Elias | [7 empty] | Launched 15 Jul (F&F/ETB). Baseline first, then set the target with Ivan.
actual | [8 empty] | -
Tier 0, PBT per line (PHP M, from Nhat's model)
Line | Phase | PM (context) | Jul | Aug | Sep | Oct | Nov | Dec | YTD att. | Basis / notes
QRPh | Star | w/ Nhat | [7 empty] | From Nhat's model once live.
actual | [8 empty] | -
Online | Maintain | w/ Nhat | [7 empty] | From Nhat's model once live.
actual | [8 empty] | -
Moto / Deals | Question | w/ Nhat | [7 empty] | Phase says push volume, watch NPM.
actual | [8 empty] | -
Credit Line | New launch | w/ Nhat | [7 empty] | Model rows live post-launch.
actual | [8 empty] | -
Solar | Question | w/ Nhat | [7 empty] | Kill or keep decision pending.
actual | [8 empty] | -
Offline | Cash cow | w/ Nhat | [7 empty] | Maintain, no PM by design.
actual | [8 empty] | -
Milestones (dates, not monthly numbers)
Milestone | Owner | Due | Done | Notes
CL: Gorg comment list turned into a checklist, validated 1:1 | Elias + Kurt | 2026-07-22 |  | Every item closed before scale-up. Do not abandon the child (Ivan).
CL: iOS bugs fixed and apps submitted (Renata) | Elias | 2026-07-21 |  | 6 iOS bugs found; fix committed same day.
Card: bureau decision one-pager (IDEMIA vs MM, like for like) | Kurt + Elias | 2026-07-24 |  | Rule: apples to apples, go cheaper. Share transparently.
Card: Amar meeting, raise 60-day clause carefully | Ivan + Kurt | 2026-07-24 |  | Signed 15 Jun. Some of their integrations were late too; do not be harsh.
Deals: cheapest-first sorting on listing | Anton | 2026-07-24 |  | From Ivan: P9,999 shows first, popular P1,000 last today.
Deals: Maxicare marketing plans switched on | Anton + Manzil | 2026-07-24 |  | Internal comms + PR aimed at investors and future Deals partners.
Retro scorecard run, past 3 months, all 5 PMs | Kurt | 2026-07-24 |  | Do not wait for December (Ivan). Calibrate to a 1-5 score.
Solar: kill-or-keep decision | Anton |  |  | Per KPI tab D3.
CL utilization target set with Ivan | Elias + Kurt | 2026-08-15 |  | 30 days post-launch.
PBT-per-line model live, monthly | Nhat |  |  | Reconciling to actuals.
Metric-tree dashboard (Tier 1-3) | Jenny |  |  | One source for this tab.

## JV
JV: edit only this tab. Yellow = fill me (Impact, Added and Due before In Progress; Delivered when shipped; update Resyncs when work bounces back).
Project | Status | Priority | KPI Key Driver | Impact (bottom-up) | Added | Due | Delivered | Speed | Resyncs | Summary | ClickUp / BRD Link
SAP Video Capture | In Progress | Urgent | SAP - D2 Disbursement per active agent | [6 empty] | Video statement capture for high-risk clients with AI transcript + facial verification. Phase 1 live. AI status update pending. | https://app.clickup.com/t/86ewdm810
Motorcycle Loans (KServico) | In Progress | High | Motorcycles - D1 Moto monthly disbursement | Moto monthly run rate, gated by Nhat | [5 empty] | Addendum & SA guide done, delivered via SAP. refresher pending. return-config changes being finalized. | https://app.clickup.com/t/9008174123/86ey83p6c
Promoter Referral Program v2: Online Linking | In Progress | Normal | SAP - D2 Disbursement per active agent | [6 empty] | Extends referral program to online transactions. BRD in progress. validation shifting to Merchants/Billease. | https://app.clickup.com/9008174123/v/dc/8cevn1b-45778/8cevn1b-224358
Feedback Form for Non-Converted Sign-ups | In Progress | Normal | SAP - D2 Disbursement per active agent | [6 empty] | Captures friction on agents' unconverted leads (25%). Adding conditional-question feature. | https://app.clickup.com/t/86ewphrkt
SAP Calculator | In Progress | Normal | SAP - D2 Disbursement per active agent | [6 empty] | Real-time SAP loan calculator from product config (40%). Mockup + ticket done. dev pending. | https://app.clickup.com/t/86ex68cg9
SAP Looker Dashboard | In Progress | Normal | BI - Jenny Ho (D1 dashboard) | [6 empty] | Looker reporting for Trx Requests, Non-Converted Sign-ups & future SAP projects (50%). Dev pending. | https://app.clickup.com/t/86ewqfqqa
SAP Announcement & Quiz Module v2 | In Progress | Low | SAP - D2 Disbursement per active agent | [6 empty] | v1 enhancements: editable-after-activation, duplicate forms, data filter by TL & SFT.
SAP Announcement & Quiz Module v1 | Completed | Urgent | SAP - D2 Disbursement per active agent |  |  |  | 2026-07-03 | - |  | Mandatory in-SAP info delivery + retention quiz per agent. Rolled to prod Jul 3. | https://app.clickup.com/t/9008174123/86ey0ujv3
Early Upsell | Completed | Urgent | SAP - D2 Disbursement per active agent | [6 empty] | Post-disbursement upsell leaflet + announcement/quiz. Live. ~94% completion as of Jul 10.
Credit Line - Agent Announcement (SAP) | Completed | Urgent | SAP - D2 Disbursement per active agent |  |  |  | 2026-07-16 | - |  | Credit Line announcement + quiz delivered to agents via SAP Jul 16.
Promoter Referral Program v1: Offline Linking | Completed | High | SAP - D2 Disbursement per active agent | [6 empty] | Auto-rewards promoters for merchant-loan referrals (offline). Live. Giftaway credits monitored weekly. | https://app.clickup.com/9008174123/v/dc/8cevn1b-45778/8cevn1b-219678

## Anton
Anton: edit only this tab. Yellow = fill me (Impact, Added and Due before In Progress; Delivered when shipped; update Resyncs when work bounces back).
Project | Status | Priority | KPI Key Driver | Impact (bottom-up) | Added | Due | Delivered | Speed | Resyncs | Summary | ClickUp / BRD Link
Item-Based Pricing | Blocked | Urgent | Pricing - Merchants (Chi) | [6 empty] | Apply promo rules to selected products, not whole catalog. Part of products engine. awaiting merchant requirements. | https://app.clickup.com/t/86ewdm7xz
Special Deals Offer to Low-Risk Customers | In Progress | High | Deals - D1 Monthly disbursement | Conversion lift on low-risk base, size with Nhat before comms |  | 2026-07-20 |  |  |  | Additional-limit offer to low-risk clients to lift conversion. DE deployed. comms Jul 20. | https://app.clickup.com/t/9008174123/86exz94uf
Deals API Documentation | In Progress | High | Deals - D1 Monthly disbursement | [6 empty] | Gather partner API docs (Giftaway, 3Cat) to scope integration timeline. | https://app.clickup.com/t/9008174123/86ey90pqa
Vouchers on Deals | In Progress | High | Deals - D1 Monthly disbursement | [6 empty] | Enable voucher purchases on Deals. preparing rails. | https://app.clickup.com/t/9008174123/86eyadmt7
Launch Deals on Web | In Progress | High | Deals - D3 Delivery on roadmap | [6 empty] | Web version of Deals. Phase 1 UI testing paused as of Jul 15.
Deals UX Study | In Progress | Normal | Deals - D2 Acceptance/conversion | [6 empty] | UX study: brand-first vs agnostic Deals store. Regroup call scheduled.
Multi-item per Merchant | In Progress | Normal | Deals - D1 Monthly disbursement | [6 empty] | Same product across merchants with price-comparison screen. BRD drafted. design pending. | https://app.clickup.com/t/9008174123/86ey9gdq1
Location-Based Delivery | In Progress | Normal | Deals - D1 Monthly disbursement | [6 empty] | Support coordinates + flag out-of-range deliveries. BRD + mockup for Kurt's input. | https://app.clickup.com/t/9008174123/86eyavqf4
Pick-Up Model | In Progress | Normal | Deals - D1 Monthly disbursement | [6 empty] | Pickup-location fulfillment option instead of delivery. BRD + mockup for Kurt's input. | https://app.clickup.com/t/9008174123/86eyavtqg
Support for Pre-Owned on Deals | Not Started | Normal | Deals - D1 Monthly disbursement | [6 empty] | Prepare rails for pre-owned listings (3Cat). Rails list being scoped. | https://app.clickup.com/t/9008174123/86eyafcd5
Credit Line for Deals | Not Started | Normal | Deals - D1 Monthly disbursement | [6 empty] | Integrate Deals with Credit Line. Target August. | https://app.clickup.com/t/9008174123/86ey7mar5
Deals 360 Dashboard | Not Started | Normal | BI - Jenny Ho (D1 dashboard) | [6 empty] | Expanded Deals 360 dashboard. requested columns from Jenny. | https://app.clickup.com/t/9008174123/86ey90puc
Adding Pay Later on Deals | Cancelled | Low | Deals - D1 Monthly disbursement | [6 empty] | Pay Later / convert-to-installment on Deals. Cancelled - redundant with Credit Line. | https://app.clickup.com/t/9008174123/86ew51ha3
Apply Promo at Category/Item Level | Cancelled | Low | Deals - D1 Monthly disbursement | [6 empty] | Item/category-level promos. Deferred - to be built after the Product Engine (Chi). | https://app.clickup.com/t/9008174123/86ey2gvyt

## Manzil
Manzil: edit only this tab. Yellow = fill me (Impact, Added and Due before In Progress; Delivered when shipped; update Resyncs when work bounces back).
Project | Status | Priority | KPI Key Driver | Impact (bottom-up) | Added | Due | Delivered | Speed | Resyncs | Summary | ClickUp / BRD Link
Deals Merchant BD Pipeline | In Progress | High | Deals BD - D2 New merchants live & disbursing | New merchants live and disbursing, ticket uplift | [5 empty] | Brand pipeline. WARM: Kimstore, 3Cat, Hati, Laptop Factory, Samsung, PrimerGrp, PowerMac, AirAsia, Qoala. Rejected: MetroMart, Engkanto, DataBlitz, Vivo, Mandaue Foam. | https://docs.google.com/spreadsheets/d/1Qx9NB9uO7TvVACgTXQszWOwBFCa_OTElUIsEwWYCVOM/
Adding Missing Deals Items | In Progress | Normal | Deals BD - D2 New merchants live | [6 empty] | Add products missing from Deals inventory. List provided. items pending.
Maxicare PRIMA Launch on Deals | Completed | High | Deals BD - D2 New merchants live |  |  |  | 2026-07-10 | - |  | Maxicare PRIMA live on Deals Jul 10. first marketing blast Jul 21. iOS pending shorter descriptions.

## Elias
Elias: edit only this tab. Yellow = fill me (Impact, Added and Due before In Progress; Delivered when shipped; update Resyncs when work bounces back).
Project | Status | Priority | KPI Key Driver | Impact (bottom-up) | Added | Due | Delivered | Speed | Resyncs | Summary | ClickUp / BRD Link
Credit Line (Launch) | In Progress | Urgent | Credit Line - D1 Utilization & drawdown | CL utilization and drawdown, target set ~30 days post-launch | [5 empty] | Launched 15 Jul (F&F/ETB). Phase-1 open: repayment/statement emails, eligibility, biz events, web FAQ, pending-txn spec. Refund/chargeback & IPP later phases. | https://app.clickup.com/t/9008174123/86eyaav7k
Access Card | In Progress | High | Card - D2 Card unit economics | Per-card break-even on interchange at target CAC | [5 empty] | BillEase Mastercard (numberless) w/ AUB & MatchMove. MOA negotiation (audit cap, CS cert, VAPT). design + bureau RFPs out. activation BRD done. Target prod Q4 2026. | https://docs.google.com/spreadsheets/d/1Vf8kaBSoQp1PeSw156nCNtYON_3ZJM5ZbR9xZPe8SjU/
Risk-Based Pricing | Blocked | High | Pricing - Merchants/Risk | [6 empty] | Dynamic interest rates by client credit behaviour. Part of products engine. awaiting requirements. | https://app.clickup.com/t/86ewn2hpd

## Jastin
Jastin: edit only this tab. Yellow = fill me (Impact, Added and Due before In Progress; Delivered when shipped; update Resyncs when work bounces back).
Project | Status | Priority | KPI Key Driver | Impact (bottom-up) | Added | Due | Delivered | Speed | Resyncs | Summary | ClickUp / BRD Link
SM Appliances - Acknowledgement Receipt | In Progress | High | Merchant Onboarding - D2 Onboarding cycle time | [6 empty] | Read-only approved-transaction receipt for merchants (75%). Dev done. awaiting SM signatory. | https://app.clickup.com/t/86ewpkfpv
Supervisors/RMs Stamp in Create Trx Report | In Progress | High | Merchant Onboarding - D2 Onboarding cycle time | [6 empty] | Adds supervisor/RM stamp to Create Trx Report (83%). Live for txns after Jun 16. validating incentives. | https://app.clickup.com/t/86ex68b0u
QRPh Chargeback Escalation (Netbank/AUB) | In Progress | High | QRPh - D1 Monthly disbursement run rate | Protects the QRPh run rate | [5 empty] | Daily QRPh chargeback escalation & checking for AUB and Netbank. | https://app.clickup.com/t/9008174123/86ey9ztg7
Merchant Onboarding Ops Queue (BAU) | In Progress | High | Merchant Onboarding - D2 Onboarding cycle time | [6 empty] | Daily BAU queue: shop/user/bank adds, onboarding, branch/name changes. ~20+ tickets/week, mostly same/next-day. | https://docs.google.com/spreadsheets/d/1FXbhtIl3aNyH9zr5Zf_xpV_OaLrUeQVwTLEMQKsn_dg/
Product Pricing / SAP Calculator PVT | In Progress | High | IT/PVT - Billy (D1 release quality gate) | [6 empty] | Pricing/tenor/IR validation across merchant scenarios (Android/iOS). Recent Fails at FC Home Lubao 3 & Shaw need config fix. | https://docs.google.com/spreadsheets/d/178O3aMK18zV_j96Xbp6UD3-QWxWX9QIFjTOju0fw-sM/
Integrate Merchant Guide to Billease Docs | Not Started | Normal | Merchant Onboarding - D2 Onboarding cycle time | Fewer onboarding tickets via self-serve guide | [5 empty] | Single self-service Merchant Guide: handbook + 7 walkthroughs, vector screens, PII redaction. Target 30% fewer tickets. | https://app.clickup.com/t/9008174123/86exz70h6
Automate Onboarding Email | Not Started | Normal | Merchant Onboarding - D2 Onboarding cycle time | [6 empty] | Auto welcome email on first transition to Active (once only), with logging + retry. | https://app.clickup.com/t/9008174123/86ev2ktw2
Update 'How to Become a Merchant' Page | Not Started | Normal | Merchant Onboarding - D2 Onboarding cycle time | [6 empty] | Add rejection screen linking to QRPh FAQs. keep success screen largely the same. | https://app.clickup.com/t/9008174123/86ey3qbz2

## KPI Key Drivers
KPI Key Drivers, per owner (delivery-first, per the Jul call with Ivan)
Scored: delivery Speed and Quality against the seniority bar. Context: the line numbers every PM must know cold (management-owned, not punished on). Growth: initiative, assessed for development, not bonus.
Owner | Context: lines and numbers to know cold | Scored: Speed | Scored: Quality | Growth: Initiative
Anton Betia | Deals and Solar: monthly disbursement at positive NPM (staged ramp TBD), acceptance and conversion, reject-salvage plan. Think like a marketer: D2C, self-service, drive own inventory. | Agreed steps delivered on time or faster (auto-scored on the tracker) | Delivered at the level expected for the bar, thought through, minimal resyncs | Connects the numbers to actions; brings prioritized initiatives (logged)
Manzil Balani | Deals BD: managed accounts (ProTech, Maxicare, 3Cat), new merchants live and disbursing, ticket uplift (TBD). National coverage per partner, else regional deals. | Agreed steps delivered on time or faster (auto-scored on the tracker) | Delivered at the level expected for the bar, thought through, minimal resyncs | Connects the numbers to actions; brings prioritized initiatives (logged)
JV Manlangit | Motorcycles and SAP: Moto monthly disbursement (TBD, gated by Nhat), disbursement per active sales agent (TBD). | Agreed steps delivered on time or faster (auto-scored on the tracker) | Delivered at the level expected for the bar, thought through, minimal resyncs | Connects the numbers to actions; brings prioritized initiatives (logged)
Elias Marcella | Credit Line and Card: CL utilization and drawdown (set ~30 days post-launch), card unit economics (CAC target TBD). Senior bar: tasks arrive fully thought through. | Agreed steps delivered on time or faster (auto-scored on the tracker) | Delivered at the level expected for the bar, thought through, minimal resyncs | Connects the numbers to actions; brings prioritized initiatives (logged)
Jastin Lagumbay | QRPh and Merchant Onboarding: QRPh run rate (TBD, star line), onboarding cycle time, zero config errors. | Agreed steps delivered on time or faster (auto-scored on the tracker) | Delivered at the level expected for the bar, thought through, minimal resyncs | Connects the numbers to actions; brings prioritized initiatives (logged)
Nhat Phan | Unit economics and P&L: PBT-per-line model live monthly, pricing and repricing coverage, every launch gated pre-launch. | Agreed steps delivered on time or faster (auto-scored on the tracker) | Delivered at the level expected for the bar, thought through, minimal resyncs | Connects the numbers to actions; brings prioritized initiatives (logged)
Jenny Ho | Business Intelligence: metric-tree dashboard live and automated (Tier 1 to 3, one source), reporting turnaround. | Agreed steps delivered on time or faster (auto-scored on the tracker) | Delivered at the level expected for the bar, thought through, minimal resyncs | Connects the numbers to actions; brings prioritized initiatives (logged)
Billy Quiambao | IT Support and PVT: release quality gate (PVT pass rate, defects caught pre-prod), support TAT within SLA. | Agreed steps delivered on time or faster (auto-scored on the tracker) | Delivered at the level expected for the bar, thought through, minimal resyncs | Connects the numbers to actions; brings prioritized initiatives (logged)
Targets and monthly actuals live on the KPI Targets H2 tab. Speed and Resyncs are captured per project on the tracker. Delivery scores and initiative log are kept by Kurt in the separate Delivery Scoreboard file.